**Healthwatch Sandwell HAB Action Log 4 July 2023**

| **HAB Date** | **Agenda Item** | **Action Point** | **Lead** | **Due Date** | **Status** | **Progress**  |
| --- | --- | --- | --- | --- | --- | --- |
|  |
| 04.07.23 | **5** | **Work Programme – Priority Projects** Discuss how best to ensure that future reports are recognised at HWBB, Scrutiny board and Health and Care Partnership Board in the future | AF/PG  | Immediate  | Completed | Standing agenda Item at HWBB.Reports to be tabled at Scrutiny Board and HCPB in the future  |
| 04.07.23 | **5** | **Work Programme – Priority Projects** Overview of the diabetes project to TF  | SS | Immediate  | Competed | Focus group held at St. Albans  |
| 04.07.23 | **5** | **Work Programme – Community Outreach** Share GP show case feedback document with board when it becomes available | ME | By end September 2023 | Pending  | Tabled at public meeting 24.10.23 |
| 04.07.23 | **5** | **Work Programme Enter and View**Send TF information about Enter and View and the statutory responsibilities HW has.  | AA | By end of July 2023 | Completed | Sent 04.07.23 |
| 04.07.23 | **5** | **Work Programme - Volunteers** Send PJ and TF promotional information re youth volunteering | AA |  By end of September  |  Pending  |  Already to go to PJ & TF but waiting for the youth providers to action. |